## National Legislation
Bahrain NAPHS 2019-2023
PREVENT
TECHNICAL AREA | NATIONAL LEGISLATION, POLICY AND FINANCING
GOAL | States Parties to have an adequate legal framework to support and enable the implementation of all of their obligations and rights to comply with and implement the IHR (2005). In some States Parties, implementation of the IHR (2005) may require new or modified legislation. Even where new or revised legislation may not be specifically required under the State Party’s legal system, states may still choose to revise a few legislations, regulations or other instruments in order to facilitate their implementation and maintenance in a more efficient, effective or beneficial manner. State Parties to ensure the provision of adequate funding for IHR implementation, through the national budget or another mechanism.
JEE Recommendations | • Establish an intersectoral working group, facilitated by WHO, composed of legal advisors and public health officials from all sectors involved in IHR implementation, to conduct an assessment of all existing national legislation,1 regulations and other instruments covering all related issues and IHR functions. • Adopt any revised and/or new legislation, including the currently pending draft Public Health Act.
JEE Indicator | P.1.1 | Legislation, laws, regulations, administrative requirements, policies or other government instruments in place for implementation of IHR.
JEE Scores | 2
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 1.1.1.1 | update the establised IHR commitee to include legal advisors and public health officials from all sectors involved in IHR implementation, | Routine Activity (NO COST) | IHR focal /other relevent sectors | WHO | No | National | realease of new committee | 1 | bar: 2019 Q4
| 1.1.1.2 | Empower both high level and technical working groups through development of formal notification procedures to 1.1.1 that could trigger changes to legislation to allow implementation of IHR activities | Routine Activity (NO COST) | IHR focal /other relevent sectors | ALL IHR bound sectors | Yes | National | New legislation. Formal notification procedures are in place. | 1 | bar: 2019 Q4 to 2020 Q2; 2021 Q1; 2022 Q1; 2023 Q1
JEE Indicator | P.1.2 | The state can demonstrate that it has adjusted and aligned its domestic legislation, policies and administrative arrangements to enable compliance with the IHR (2005)
JEE Scores | 2
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators | Periodicity | 2019 Q1: Implementation
|  |  |  | for Implementation including budget line holder |  |  |  | (Monitoring and Evaluation) |  | 2019 Q1: 2019; 2020 Q1: 2020; 2021 Q1: 2021; 2022 Q1: 2022; 2023 Q1: 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 1.2.1.1 | Adopt any revised and/or new legislation, including the currently pending draft Public Health Act.and ministreal order to lgalise IHR document | Routine Activity (NO COST) | legal affairs at MOH/Public health | other relevent sectors | No | National | realese of ministreal order to lgalise IHR document | 1 | [20 empty] | Public health Law relased in 2018 | bar: 2020 Q1

## IHR Coordination
Bahrain NAPHS 2019-2023
PREVENT
TECHNICAL AREA |  | IHR COORDINATION, COMMUNICATION AND ADVOCACY
GOAL | The national IHR focal point to be accessible at all times to communicate with the WHO regional IHR contact points and with all relevant sectors and other stakeholders in the country. States Parties to provide WHO with contact details of their national IHR focal points, as well as continuously update and annually confirm them.
JEE Recommendations | • Ensure sustainability of the IHR and NFP functions through continuous high-level political and administrative support from all stakeholder sectors. • Evaluate the efficiency of the IHR NFP in collaboration with the MOH, WHO and national stakeholders. • Ensure 24/7 IHR duty implementation
JEE Indicator | P.2.1 | A functional mechanism is established for the coordination and integration of relevant sectors in the implementation of IHR
JEE Scores | 5
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 2.1.1.1 | Develop generic email that will be coverred 24/7 by National focal point staff | Routine Activity (NO COST) | IHR focal | MOH techinical supporting group | No | National | development of email | 1 | bar: 2020 Q2
| 2.1.1.2 | Evaluate the efficiency of the IHR NFP in collaboration with the MOH, WHO and national stakeholders. | SimEX, TTX | IHR focal /relevent sectors/stakeholders | WHO | yes | National | simulation exercise done/testing of NFP through real situation | 1 | [20 empty] | Bahrain participate on the online simulation exercise | bar: 2020 Q2

## AMR
Bahrain NAPHS 2019-2023
PREVENT
TECHNICAL AREA |  | ANTIMICROBIAL RESISTANCE
GOAL | Support work coordinated by the FAO, OIE and WHO for developing an integrated and global package of activities to combat antimicrobial resistance, spanning human, animal, agricultural, food and environmental aspects (i.e. a One-health approach). This would include: (i) having a national comprehensive plan for each country to combat antimicrobial resistance; (ii) strengthening of surveillance and laboratory capacity at the national and international levels following agreed upon international standards developed in the framework of the Global Action Plan; and (iii) improved conservation of existing treatments and collaboration to support the sustainable development of new antibiotics, alternative treatments, preventive measures and rapid, point-of-care diagnostics with systems to preserve new antibiotics.
JEE Recommendations | • Develop a national plan incorporating AMR detection, reporting, surveillance and antimicrobial stewardship programmes through engagement of stakeholders representing human health, animal, food, agriculture and environment sectors• Formalize an organizational structure to manage and coordinate AMR activities. • Assign a national AMR reference laboratory for Bahrain. • Enhance AMR active surveillance capacity and prevention by implementing effective stewardship programmes in both the human and animal health sectors. • Strengthen interagency collaboration to enhance national AMR reporting between the human health and animal sectors.
JEE Indicator | P.3.1 | Antimicrobial resistance detection
JEE Scores | 3
Objective
| # | Summary of Planned Activities | activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 3.1.1.1 | Improve the Central PH and Veterinary Laboratories infrastructure to provide quality support for AMR | Infrastucture investement - Large | MOH , MoA, RSS, Zoonotic disease , food safety | OIE/WHO/FAO | yes | National | No. of accredited labs | 1 | bar: 2020 Q4
| 3.1.1.2 | Designation of national AMR Reference laboratory | Infrastructure/Supplies Investment, LARGE | MOH | N/A | No | National | ministerial decree | 1 | bar: 2019 Q2
JEE Indicator | P.3.2 | Surveillance of infections caused by resistant pathogens
JEE Scores | 3
Objective
| # | Summary of Planned Activities | activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 3.2.1.1 | Establish a national AMR surveillance system within the national surveillance system that is coordinated between the two sectors | Infrastucture investement - Large | MOA\ MOH | OIE/WHO, FAO | Yes | National & Subnational | System is established/Data is coordinated and shared between both sectors | 1 | bar: 2020 Q4
| 3.2.1.2 | Develop training programs on joint surveillance and response activities | Workshop/Training, MEDIUM | MOA\ MOH | OIE/WHO, FAO | Yes | National | Training Program is developed/Number of trainees | 5 | bar: 2019 Q2; 2020 Q2; 2021 Q2; 2022 Q2; 2023 Q2
| 3.2.1.3 | improve the capacities of microbiology laboratories in the private sector | Workshop/Training, MEDIUM | MOH/NHRA | N/A | No | National & Subnational | Antimicrobial Consumption and other antionla qaulity indicators | 5 | [20 empty] | also by supervisory visits | bar: 2019 Q4; 2020 Q4; 2021 Q4; 2022 Q4; 2023 Q4
JEE Indicator | P.3.3 | Healthcare associated infection prevention and control programmes
JEE Scores | 5
Objective
| # | Summary of Planned Activities | activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 3.3.1.1 | improving National coordination of IPC programmes | Workshop/Training, MEDIUM | MOH | OIE/WHO | Yes | National & Subnational | Antimicrobial Consumption and other antionla qaulity indicators | 5 | bar: 2019 Q1; 2020 Q1; 2021 Q1; 2022 Q1; 2023 Q1
| 3.3.1.2 | developing IPC SOP/s | Routine Activity (NO COST) | MOH | WHO | No | National & Subnational | Antimicrobial Consumptionand other antionla qaulity indicators | 1 | bar: 2021 Q4
JEE Indicator | P.3.4 | Antimicrobial stewardship activities
JEE Scores | 2
Objective
| # | Summary of Planned Activities | activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 3.4.1.1 | Implementing effective stewardship programmes in both the human and animal health sectors | Working Group Meeting | MOH/MOA | WHO/OIE/FAO | yes |  | National AMR Steering com. established Stewardship programs Activated at all levels with all agreed on antionla quality indicators | 20 | bar: 2019 Q1 to 2023 Q4

## Zoonotic Disease
Bahrain NAPHS 2019-2023
PREVENT
TECHNICAL AREA | ZOONOSES
GOAL | Adopt measured behaviours, policies and/or practices that minimize the transmission of zoonotic diseases from animals into human populations.
JEE Recommendations | • Establish a formal mechanism among relevant stakeholders for regular communication, collaboration, and science-based decision-making for the prevention, detection and response to zoonotic diseases. • Develop a list of priority zoonotic diseases jointly agreed on by both the public health and animal sectors. • Develop and test a joint national plan for response to zoonotic diseases (including information sharing, joint risk assessment and decision-making).• Increase the human resource and technical capacity in epidemiology and zoonotic diseases in the Veterinary Directorate. • Increase the capacity at the CVL for specific priority zoonoses.
JEE Indicator | P.4.1 | Surveillance systems in place for priority zoonotic diseases/pathogens
JEE Scores | 3
Objective
| # | Summary of Planned Activities | activity type | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 4.1.1.1 | Establish National working group (One Health) with specific ToRs and SOPs to review National legislation to facilitate implementation of IHR in animal health sector | Routine Activity (NO COST) | MoWM/ MOH and All relevant sectors | Supreme council of environment | Yes | National | Committee is established | 1 | bar: 2020 Q2
| 4.1.1.2 | Consultation meeting to discuss development of electronic information sharing platform data sharing between surveillance in both animal and public health sectors | Working Group Meeting | MoWM/MOH, Comm in 4.1.1.1 | WHO/FAO/OIE | Yes | National | Information sharing structure is finalized | 1 | bar: 2020 Q2
| 4.1.1.3 | Develop List of priority of zoonotic diseases | Working Group Meeting | MoWM and All relevant sectors | MOH/OIE | No | National | List of zoonotic diseases | 1 | bar: 2020 Q2
| 4.1.1.4 | Build capacity of CVL lab | Infrastructure/Supplies Investment, LARGE | MoWM | OIE | Yes | National | CVL lab increase capacity | 1 | bar: 2020 Q2
JEE Indicator | P.4.2 | Veterinary or animal health workforce
JEE Scores | 3
Objective
| # | Summary of Planned Activities | activity type | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 4.2.1.1 | Review the current employment policies to be more attractive and achieve adequate retention of qualified staff. | Consultancy - NATIONAL | MoWM | CSB | Yes | National | establishment of epidemiological unit +retention policies are endorsed + Employment Survey quality improved | 10 | bar: 2020 Q2
JEE Indicator | P.4.3 | Mechanisms for responding to infectious zoonoses and potential zoonoses are established and functional
JEE Scores | 4
Objective
| # | Summary of Planned Activities | activity type | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 4.3.1.1 | Preparing national plan for zoonotic diseases | Working Group Meeting | MoWM/ MOH | one healthworking group , PLAN to form national plan for zoonotic diseases | Yes | National | National Plan is developed | 10 | bar: 2020 Q2

## Food Safety
Bahrain NAPHS 2019-2023
PREVENT
TECHNICAL AREA | FOOD SAFETY
GOAL | State Parties to have surveillance and response capacity for risk or events related to food- and water-borne diseases, with effective communication and collaboration among the sectors responsible for food safety and safe water and sanitation.
JEE Recommendations | • Accelerate endorsement of the food safety provisions in the new Public Health Law and related administrative measures.• Establish an integrated/unified national food safety system/authority including a 3–5-year action plan with allocated resources and defined roles and responsibilities. • Map current roles and responsibilities for managing food safety, including assessment, inspection, testing, traceability and recall functions. • Establish an electronic reporting system as part of the current public health system for reporting and managing events. • Strengthen communication and data sharing between relevant agencies and consider establishing an International Food Safety Authorities Network (INFOSAN) structure at national level.
JEE Indicator | P.5.1 | Mechanisms are established and functioning for detecting and responding to foodborne disease and food contamination.
JEE Scores | 4
Objective
| # | Summary of Planned Activities | activity type | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 5.1.1.1 | Proposal of National food safety committee submitted to legal affaire Strengthen communication and data sharing between relevant agencies and consider establishing an International Food Safety Authorities Network (INFOSAN) structure at national level. | Routine Activity (NO COST) | food control section/MOH | MoWM/MOIC/Customs / chamber of commerce | No | Nationa/Subnational | Approval of committee | 1 | bar: 2021 Q1
| 5.1.1.2 | Establish national food safety action plan with integration of GCC food safety action paln | Routine Activity (NO COST) | food control section/MOH | MoWM/MOIC/Customs / chamber of commerce | No | Nationa/Subnational | implmw=entation of the action plan | 1 | bar: 2020 Q4
| 5.1.1.3 | Establish electronic system for managing food safety, including assessment, inspection, testing, traceability and recall functions | Investigative Activity - MEDIUM | food control section/MOH | MoWM/MOIC/Customs / chamber of commerce | Yes | Nationa/Subnational | implementation of Electronic food safety system | 1 | bar: 2020 Q1
| 5.1.1.4 | Utlize the GCC electronic reporting system for reporting and managing events | Routine Activity (NO COST) | food control section/MOH |  | No | Nationa/Subnational | implementation of GCC electronic allert system for food GRARSF | 1 | bar: 2019 Q1 to 2023 Q4

## BioSafety BioSecurity
Bahrain NAPHS 2019-2023
PREVENT
TECHNICAL AREA | BIOSAFETY AND BIOSECURITY
GOAL | A whole-of-government national biosafety and biosecurity system is in place, to ensure that: especially dangerous pathogens are identified, held, secured and monitored in a minimal number of facilities according to best practices; biological risk management training and educational outreach are conducted to promote a shared culture of responsibility, reduce dual use risks, mitigate biological proliferation and deliberate use threats, and ensure safe transfer of biological agents; and country-specific biosafety and biosecurity legislation, laboratory licensing and pathogen control measures are in place as appropriate.
JEE Recommendations | • Enact comprehensive national biorisk legislation covering both biosafety and biosecurity in laboratories across government sectors. • Develop a national plan for the implementation of the biorisk legislation. • Expand and publish an inventory of the agents/pathogens of concern, conduct risk assessments and implement mitigation plans in the facilities housing those agents. • Ensure sufficient human resources by appointing biosafety and biosecurity officers in all microbiology laboratories. • Strengthen training in both biosafety and biosecurity for all laboratories across government sectors.
JEE Indicator | P.6.1 | Whole-of-government biosafety and biosecurity system is in place for human, animal and agriculture facilities
JEE Scores | 4
Objective
| # | Summary of Planned Activities | activity type | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 6.1.1.1 | collaboration between relevent sakeholder to enact comprehansive national biorisk legislation | Working Group Meeting | Supreme Council of Health,national health laboratories biosatey commmittee,superem counsil for environment,NHRA | MOH, NHRA | No | National | Biosafety & biosecuritylegislation | 6 | bar: 2019 Q1; 2019 Q4; 2020 Q2 to 2021 Q1
| 6.1.1.2 | to develop a national plan for the implementation of the biorisk legislation | Working Group Meeting | Supreme Council of Health,national health laboratories biosatey commmittee,superem counsil for environment,NHRA | CDC, PHL, SMC, BDF, KHUH | yes | National | formulation of National plan | 4 | bar: 2021 Q3 to 2022 Q2
| 6.1.1.3 | To generate a list of agents/pathogens of concern from all eelevent sector | Routine Activity (NO COST) | Supreme Council of Health,national health laboratories biosatey commmittee,superem counsil for environment,NHRA | CDC, PHL, SMC, BDF, KHUH | No | National | Expanded and published list | 1 | bar: 2019 Q4
| 6.1.1.4 | To conduct risk assessment and implement mitigation plans in the facilities housing those agents | Workshop/Training, MEDIUM | Supreme Council of Health,national health laboratories biosatey commmittee,superem counsil for environment,NHRA | WHO + OIE | Yes | National | Completing the risk assesment and mitigation plans | 1 | bar: 2019 Q4; 2021 Q4
JEE Indicator | P.6.2 | Biosafety and biosecurity training and practices
JEE Scores | 4
Objective
| # | Summary of Planned Activities | activity type | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 6.2.1.2 | Develop a sustained academic training program on biosafety and biosecurity through the university. | Develop Curriculum/Training Programme, SMALL | university of Bahrain, RCSI, AGU | MOH, Directorate of higher education | yes | National | Accredited training program / chapters in Biosafety and biosecurity | bar: 2021 Q3
| 6.2.1.3 | Estublishing a sustainable training in biosafety and biosecurity in the private sector | Workshop/Training, MEDIUM | MOH, NHRA | private labs | No | National | Training records of the laboratory staff | bar: 2020 Q2 to 2020 Q3

## Immunization
Bahrain NAPHS 2019-2023
PREVENT
TECHNICAL AREA | IMMUNIZATION
GOAL | to maintain EPI vaccine coverage >95% natonal & sub nationallevel 2. To ensure following the National vaccine access and delivery system & guidelines for cold chain. 3.To expand the vaccine coverage to other target
JEE Recommendations | • Maintain the current high vaccination coverage, low incidence of vaccine preventable diseases and high public trust in the NIP. • Continue with the electronic data transfer and interlinked registries to ensure real-time follow-up analyses of vaccination coverage, vaccine safety and delivery systems. • Maintain high quality data analysis and research activities on the impact of public health value of new vaccines introduced or considered for introduction to the NIP.
JEE Indicator | P.7.1 | Vaccine coverage (measles) as part of national programme
JEE Scores | 5
Objective 1
| # | Summary of Planned Activities | activity type | Responsible authority(s) for Implemetation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monotoring and Evaluation) | Periodicity | Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 7.1.1.1 | Develop Executive regulation and guides | Routine Activity (NO COST) | MoH | Supreme Health Council, NHRA, governmental and private health facilities, legal affairs | No | National & Subnational | Executive regulation and guide developed | 1 | bar: 2019 Q2
| 7.1.1.2 | Utilization of electronic immunization registry for continous quality improvement in relation to vaccination | Routine Activity (NO COST) | MoH | MOH and INDRA TEAM | No | National & Subnational | Meeting conducted, meeting minutes | 1 | bar: 2019 Q2
| 7.1.1.3 | update the SOP | Routine Activity (NO COST) | MOH | NHRA AND PRIVATE HEALTH FACILITIES | No | National & Subnational | SOP Development | 1 | bar: 2019 Q2
JEE Indicator | P.7.2 | National vaccine access and delivery
JEE Scores | 5
Objective 2
| # | Summary of Planned Activities | activity type | Responsible authority(s) for Implemetation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monotoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 7.2.1.1 | UPDATE VACCINATION GUIDE | Routine Activity (NO COST) | MoH | NHRA,governmental and private health facilities | IMMUNIZATION PROGRAM | National | GUIDE DEVELOPED | 1 | bar: 2019 Q2

## National Laboratory System
Bahrain NAPHS 2019-2023
DETECT
TECHNICAL AREA | NATIONAL LABORATORY SYTEMS
GOAL | Real-time bio surveillance with a national laboratory system and effective modern point-of-care and laboratory-based diagnostics in all administrative sectors supporting public health.
JEE Recommendations | • Develop a clear regulatory framework for national microbiological reference laboratories and strengthen the process for comprehensive accreditation of all microbiological laboratories. • Develop clear regulatory obligations for all microbiology laboratories to participate regularly in national or international EQA programmes as part of the licensing and auditing process. • Ensure that there are sufficient training resources for the appropriate use of microbiology laboratory tests and for implementation of national standard laboratory test algorithms in all government sectors.
JEE Indicator | D.1.1 | Laboratory testing for detection of priority diseases
JEE Scores | 5
Objective
| # | Summary of Planned Activities | activity type | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 8.1.1.2 | Drafting a national lab strategic plan | Working Group Meeting | National lab Committee | The Supreme councel of Health, MOH | No | National | National lab strategic plan | 4 | bar: 2019 Q4 to 2020 Q3
| 8.1.1.3 | Assuring Sufficient training resources for lab staff | Workshop/Training, SMALL | MOH-Training Department & NHRA | MOH & other Heath institutes managments | No | National | Training Records | 1 | bar: 2020 Q2
| 8.1.1.4 | Implementation of a national standard laboratory test algorithms in all government and privet sectors | Working Group Meeting | NHRA | All Heath institutes | No | National | SOP of the national standard laboratory tests | 2 | bar: 2020 Q2; 2020 Q4
| 8.1.1.5 | Implmentation of A national system or mechanism for quality assurance for laboratories (In Process) | Workshop/Training, MEDIUM | NHRA | All Heath institutes | No | National | NHRA - Accreditation Standards for Laboratories | 1 | bar: 2021 Q1
| 8.1.1.5.1 | Developing Auditing Program & Conducting a training course for Auditing | Workshop/Training, MEDIUM | NHRA | All Heath institutes | No | National | Workshop & Auditing reports | 1 | bar: 2021 Q2
JEE Indicator | D.1.2 | Specimen referral and transport system
JEE Scores | 5
Objective
| # | Summary of Planned Activities | activity type | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 8.2.1.1 | Nomination of microbiological refrence lab/s (NRL) | Working Group Meeting | MoH | SMC, NHRA,BDF,KHUH, PHL | No | National | Data | 2 | bar: 2020 Q2; 2020 Q4
| 8.2.1.2 | Draft NRL functions for essential pathogens | Working Group Meeting | MOH | SMC, NHRA,BDF,KHUH, PHL | No | National |  | 2 | bar: 2020 Q2; 2020 Q4
| 8.2.1.3 | Draft the monitoring policy/sops | Working Group Meeting | NHRA | SMC, NHRA,BDF,KHUH, PHL | No | National | bar: 2021 Q1; 2021 Q3
JEE Indicator | D.1.3 | Effective modern point of care and laboratory based diagnostics
JEE Scores | 4
Objective
| # | Summary of Planned Activities | activity type | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 8.3.1.1 | Training on Point-of-care testing should be considered for some diseases. | Workshop/Training, MEDIUM | MoH | NHRA | Yes | National | document of valdiation of any point of care test & document of inernal and external QC | 8 | bar: 2020 Q2; 2020 Q4; 2021 Q2; 2021 Q4; 2022 Q2; 2022 Q4; 2023 Q2; 2023 Q4
| 8.3.1.4 | Audit of Implementation of the policy | Routine Activity (NO COST) | SMC (MOH) | NHRA | No | Subnational | Audit done and action taken accordingly | 4 | bar: 2020 Q4; 2021 Q4; 2022 Q4; 2023 Q4
JEE Indicator | D.1.4 | Laboratory Quality System
JEE Scores | 4
Objective
| # | Summary of Planned Activities | activity type | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 8.4.1.1 | Develop national standard guidelines for quality standards | Working Group Meeting | NHRA | MOH , BDF, KHUH,SMC | No | National | Guidelines developed | 2 | bar: 2020 Q2; 2020 Q4
| 8.4.1.2 | Develop national standard guidelines for Microbiology labs | Working Group Meeting | National laboratories committee | MOH , BDF, KHUH,SMC and all privet labs, univercity lab, vet lab | No | National | Microbiological Standards in place | 2 | bar: 2020 Q2; 2020 Q4

## Real time Surveillance
Bahrain NAPHS 2019-2023
DETECT
TECHNICAL AREA | REAL TIME SURVEILLANCE
GOAL | Strengthened foundational indicator, and event-based surveillance systems that are able to detect events of significance for public health, animal health and health security; improved communication and collaboration across sectors and between subnational, national and international levels of authority regarding surveillance of events of public health significance; and improved country and regional capacity to analyse and link data from and between strengthened, real-time surveillance systems, incorporating interoperable, interconnected electronic reporting systems. This would include epidemiologic, clinical, laboratory, environmental testing, product safety and quality, and bioinformatics data; and advancement in fulfilling the core capacity requirements for surveillance in accordance with IHR and OIE standards.
JEE Recommendations | • Integrate the health and zoonotic surveillance systems. • Extend electronic reporting to include more surveillance sites. • Increase staff as further private health facilities are established in the country. • Provide advanced training for key staff to develop expertise in syndromes and diseases that demand further in-depth analysis. • Develop and implement guidance documents including approved guidelines and bulletins. • Engage in further coordination with GCC countries for specialized training, mentorship, and collaboration in reporting and analysis.
JEE Indicator | D.2.1 | Indicator- and event-based surveillance systems
JEE Scores | 1900-01-02
Objective
| # | Summary of Planned Activities |  | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | Implementation
|  |  | activity type | [6 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 9.1.1.1 | Conduct training workshop on data validation | Workshop/Training, SMALL | MOH | WHO | Yes | National & Subnational | Training workshops | 2 | bar: 2020 Q4; 2023 Q1
| 9.1.1.2 | develop SOPs for data validation | Routine Activity (NO COST) | MOH | WHO | Yes | National | SOPs | 1 | bar: 2021 Q2
| 9.1.1.3 | Conduct national training on event based surveillance | Workshop/Training, LARGE | MOH/IHR relevent sectors/community representitive/media reprentitive/health care representitive | WHO | yes | National & Subnational | Training workshops | 1 | bar: 2021 Q2
| 9.1.1.4 | delevop SOPs a for event –based surveillance reporting and verification to scan and monitor rumours | Routine Activity (NO COST) | MOH/IHR relevent sectors/community representitive/media reprentitive/health care representitive | WHO | yes | National & Subnational | SOPs | 1 | bar: 2021 Q3
JEE Indicator | D.2.2 | Interoperable, interconnected, electronic real-time reporting system
JEE Scores | 3
Objective
| # | Summary of Planned Activities |  | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
|  |  | activity type | [6 empty] | 2019 Q1: 2019; 2020 Q1: 2020; 2021 Q1: 2021; 2022 Q1: 2022; 2023 Q1: 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 9.2.1.1 | Add the main secondary health care hospital to the electrnic reporting system | Infrastructure/Supplies Investment, SMALL | MoH | PID,Indra | No | National | development of electronic reporting | 1 | [20 empty] | done | bar: 2019 Q1
| 9.2.1.2 | develop guideline for integrated surveillance | Working Group Meeting | MOH | animal health sector and Human health sector | Yes | National & Subnational | development of SOP | 1 | bar: 2020 Q3
JEE Indicator | D.2.3 | Analysis of surveillance data
JEE Scores | 5
Objective
| # | Summary of Planned Activities |  | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
|  |  | activity type | [6 empty] | 2019 Q1: 2019; 2020 Q1: 2020; 2021 Q1: 2021; 2022 Q1: 2022; 2023 Q1: 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 9.3.1.1 | develop SOPS for issuing integrated epidemiological Laboratory and veterinary reports | Routine Activity (NO COST) | MOH | animal control and health directorate | Yes | National & Subnational | SOPs | 1 | bar: 2019 Q3
| 9.3.1.2 | regular visit to govermental and private sectos to sensitize them to reporting | Routine Activity (NO COST) | MOH | National health regulatory authority | no | National & Subnational | visits to health sites | 5 | bar: 2020 Q4; 2021 Q4; 2022 Q4
JEE Indicator | D.2.4 | Syndromic surveillance systems
JEE Scores | 5
Objective
| # | Summary of Planned Activities |  | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
|  |  | activity type | [6 empty] | 2019 Q1: 2019; 2020 Q1: 2020; 2021 Q1: 2021; 2022 Q1: 2022; 2023 Q1: 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 9.4.1.1 | national workshop to strengthen syndromic surveillance methods | Workshop/Training, SMALL | MOH | animal control and health directorate, WHO, FAO, , CDC | Yes | National & Subnational | Workshop | 3 | bar: 2019 Q3; 2020 Q3; 2021 Q2

## Reporting
Bahrain NAPHS 2019-2023
DETECT
TECHNICAL AREA | REPORTING
GOAL | Timely and accurate disease reporting according to WHO requirements and consistent coordination with FAO and OIE.
JEE Recommendations | • Conduct simulation exercises to test the 24-hour notification of potential public health events of international concern in the country to WHO. • Establish a mechanism (online portal) for the timely notification and information sharing on such events among national stakeholders.
JEE Indicator | D.3.1 | System for efficient reporting to WHO,FAO and OIE
JEE Scores | 5
Objective 1
| # | Summary of Planned Activities | activity type | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 10.1.1.1 | simulation exercises to test the 24-hour notification of potential public health events of international concern in the country to WHO | SimEX, Functional | MOH/IHR relevent sectors | WHO, FAO, OIE,other Stakeholders | Yes | National | TORs dissemination | MOH ,WHO | [20 empty] | bahrain participate in the online SimEX done by EMRO | bar: 2020 Q2
JEE Indicator | D.3.2 | Reporting Network and Protocols in Country
JEE Scores | 4
Objective 2
| # | Summary of Planned Activities | activity type | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 10.2.1.1 | Generate email group and Whats app group for national communication and updated regularly | Routine Activity (NO COST) | MoH and other relevent sector |  | No | National & Subnational | updated Email group and whatsapp group generated | 1 | bar: 2020 Q1
| 10.2.1.2 | generate list of contacts from all relevent sectors and update it regularly | Routine Activity (NO COST) | MoH and other relevent sector |  | No | National & Subnational | updated list is available and circulated | bar: 2020 Q1

## Workforce Development
Bahrain NAPHS 2019-2023
DETECT
TECHNICAL AREA | WORKFORCE DEVELOPMENT
GOAL | State Parties to have skilled and competent health personnel for sustainable and functional public health surveillance and response at all levels of the health system and the effective implementation of the IHR (2005). Workforce to include physicians, veterinarians, biostatisticians, laboratory scientists, farming/ livestock professionals, with an optimal target of one trained field epidemiologist (or equivalent) per 200 000 population, who can systematically cooperate to meet relevant IHR and Performance of Veterinary Services core competencies.
JEE Recommendations | • Conduct simulation exercises to enhance the capacity of human resources. • Recruit additional staff based on the human resources strategy. • Develop a staff development plan and relations with teaching units to train additional staff at advanced FETP level.
JEE Indicator | D.4.1 | Human resources available to implement IHR core capacity requirements
JEE Scores | 5
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 11.1.1.1 | simulation exercises to enhance the capacity of human resources | SimEX, TTX | MOH/relevent sectors | WHO | yes | national and subnational | simulation exercise done | 2 | bar: 2020 Q4; 2022 Q4
JEE Indicator | D.4.2 | FETP or other applied epidemiology training programme in place
JEE Scores | 5
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 11.2.1.1 | to Develop a staff training plan including field / applied epidemiology | Routine Activity (NO COST) | MOH training department | all relevent department in Ministry of health | No | national | training plan including epidemiology training | 5 | bar: 2019 Q4; 2020 Q4; 2021 Q4; 2022 Q4; 2023 Q4
JEE Indicator | D.4.3 | Workforce strategy
JEE Scores | 3
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 11.3.1.1 | develop A Strategic Framework for Emergencv Preparedness including workforce | Working Group Meeting | Disaster committee | all relevent sectors | y | national and subnational | stratigic framework development | 1 | bar: 2020 Q4

## Preparedness
Bahrain NAPHS 2019-2023
RESPOND
TECHNICAL AREA | PREPAREDNESS
GOAL | Development and maintenance of national, intermediate (district) and local/primary level public health emergency response plans for relevant biological, chemical, radiological and nuclear hazards. This covers mapping of potential hazards, identification and maintenance of available resources, including national stockpiles and the capacity to support operations at the intermediate and local/primary levels during a public health emergency.
JEE Recommendations | • Review existing national and contingency emergency preparedness plans to identify any gaps. • Develop a communication strategy to inform all stakeholders, including communities, of risks. • Identify training needs, institutions, and standardization of training needs based on an assessment to harmonize the workforce development process. • Establish/strengthen a dedicated unit in MOH to improve coordination of emergency preparedness and response in health with all concerned stakeholders, and to enhance multisectoral preparedness.
JEE Indicator | R.1.1 | National multi-hazard public health emergency preparedness and response plan is developed and implemented
JEE Scores | 5
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 12.1.1.1 | To review the existing national and contingency emergency preparedness plans . | Working Group Meeting | National Disaster committee | MOH ,suprem counsil of environment and all other relevent sectors | No | National and subnational | reivewed plan | 1 | bar: 2020 Q1; 2022 Q1
| 12.1.1.2 | To review and update communication strategy for stakeholders, including communities based on mapped risk | Working Group Meeting | National Disaster committee | all relevent sectors | yes | National and subnational | reviewd communication strategy | 1 | bar: 2020 Q1; 2021 Q4; 2022 Q4; 2023 Q4
| 12.1.1.3 | To identify training needs, institutions, and standardization of training needs based on an assessment to harmonize the workforce development process. | Working Group Meeting | National Disaster committee | all relevent sectors | No | National and subnational | training needs assessment is conducted | 1 | bar: 2021 Q4
JEE Indicator | R.1.2 | Priority public health risks and resources are mapped and utilized
JEE Scores | 5
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 12.2.1.1 | to review national resourse mapping plan and update accordingly | Working Group Meeting | National Disaster committee | all relevent sectors | No | Natinal and subnational | resources mapping and update plan | 1 | bar: 2020 Q3; 2021 Q3; 2022 Q3; 2023 Q3
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4

## Emergency Response Operation
Bahrain NAPHS 2019-2023
RESPOND
TECHNICAL AREA | EMERGENCY RESPONSE OPERATIONS
GOAL | Country with public health emergency operations centre (EOC) functioning according to minimum common standards; maintaining trained, functioning, multisectoral rapid response teams and “real-time” biosurveillance laboratory networks and information systems; as well as trained EOC staff capable of activating a coordinated emergency response within 120 minutes of the identification of a public health emergency.
JEE Recommendations | • Regularly review and update the emergency response plans including hospitals (public/private) focusing on EOC functions, and ensure their dissemination among all stakeholders, particularly the incident command system. • Develop/review SOPs to operationalize the plans at all levels. • Ensure that simulations involving key stakeholders include EOCs. • Develop case management guidelines related to different hazards. • Expand risk assessments to include all IHR-related hazards.
JEE Indicator | R.2.1 | Capacity to activate emergency operations
JEE Scores | 5
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 13.1.1.1 | Training for all relevant ministries needs to be continued and include EOC members. | Workshop/Training, MEDIUM | MOH / MOI | All relevant sectors | No | National | Wel trained staff | 1 | bar: 2019 Q1
| 13.1.1.2 | developing a roster to support EOC functions | Routine Activity (NO COST) | MOH | MOH | NO | National | Emergency call out system | 1 | bar: 2019 Q1
JEE Indicator | R.2.2 | Emergency Operations Centre Operating Procedures and Plans
JEE Scores | 5
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 13.2.1.1 | deveop SOP to ensure the link between hospitals (private/public) and the national incident management system. | Routine Activity (NO COST) | MOI/ MOH | N/A | no | National | SOP developed | 1 | bar: 2019 Q1
JEE Indicator | R.2.3 | Emergency Operations Program
JEE Scores | 5
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | training for staff running the EOC at all levels in an internal capability analysis. | Small workshop/training | MOI/ MOH | N/A | National | Training Conducted | Traing Records | 2 | bar: 2019 Q1
JEE Indicator | R.2.4 | Case management Procedures CBRN
JEE Scores | 4
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | Updating the disaster plan to cover the IHR-related hazards(chemical and radiological events) | Intermediate meeting | MOI | All related Sectors | No | National | plan Updated | 1 | bar: 2019 Q1

## Linking PH and Security
Bahrain NAPHS 2019-2023
RESPOND
TECHNICAL AREA | LINKING PUBLIC HEALTH & SECURITY AUTHORITIES
GOAL | In the case of a biological event of suspected or confirmed deliberate origin, a country will be able to conduct a rapid, multisectoral response, including the capacity to link public health and law enforcement, and to provide and/or request effective and timely international assistance, such as to investigate alleged use events.
JEE Recommendations | • Improve timely information sharing related to detection of public health events, investigations and response. • Review and update existing SOPs for joint investigations and response to public health events, particularly for the private sector. • Ensure access to all existing plans by relevant stakeholders of public health and security.
JEE Indicator | R.3.1 | Public Health and Security Authorities, (e.g. Law Enforcement, Border Control, Customs) are linked during a suspect or confirmed biological event
JEE Scores | 4
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 14.1.1.1 | test SOPs for timely information sharing related to detection of public health events, investigations and response | SimEX, TTX | Disaster committee | MOH ,MOI and all relevent sectors | No | National and subnational | testing and update of SOPs | 4 | bar: 2020 Q2; 2021 Q2; 2022 Q2; 2023 Q2
| 14.1.1.2 | update existing SOPs for joint investigations and response to public health events, particularly for the private sector. | Routine Activity (NO COST) | Disaster committee | MOH ,MOI,NAHRA and all relevent sectors | No | National and subnational | updated SOPs | 2 | bar: 2020 Q1; 2022 Q1
| 14.1.1.3 | testing for all existing plans to ensure knowledge of relevant stakeholders of public health and security about the plan and their resonsibilityies . | SimEX, TTX | Disaster committee | MOH ,MOI,NAHRA and all relevent sectors | No | National and subnational | testing of existing plans | 4 | bar: 2020 Q4; 2021 Q4; 2022 Q4; 2023 Q4

## Medical Countermeasures
Bahrain NAPHS 2019-2023
PREVENT
TECHNICAL AREA | Medical Countermeasures and Personnel Deployment
GOAL | A national framework for transferring (sending and receiving) medical countermeasures and public health and medical personnel among international partners during public health emergencies.
JEE Recommendations | • Review existing plans and procedures to widen the scope to include countries outside GCC. • Strengthen cooperation and collaboration with NHRA to further improve the system of personnel deployment (sending and receiving) within the country and externally. • Review and update the vendors list according to IHR-related hazards to ensure timely and optimum support.
JEE Indicator | R.4.1 | System is in place for sending and receiving medical countermeasures during a public health emergency
JEE Scores | 5
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 15.1.1.1 | Review existing plans and procedures to widen the scope to include countries outside GCC. | Working Group Meeting | Disaster committee | MOH ,MOI and all relevent sectors | No | National and subnational | testing and update of SOPs | 2 | bar: 2019 Q1 to 2023 Q4
| 15.1.1.2 | Review and update the vendors list according to IHR-related hazards to ensure timely and optimum support. | Working Group Meeting | Disaster committee | MOH ,MOI and all relevent sectors | No | National and subnational | updated vender list | 5 | bar: 2019 Q1 to 2023 Q4
JEE Indicator | R.4.2 | System is in place for sending and receiving health personnel during a public health emergency
JEE Scores | 5
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 15.2.1.1 | Strengthen cooperation and collaboration with NHRA to further improve the system of personnel deployment (sending and receiving) within the country and externally. | Working Group Meeting | Disaster committee | MOI | no | national | SOPs for deployment | 1 | bar: 2020 Q1

## Risk Communication
Bahrain NAPHS 2019-2023
RESPOND
TECHNICAL AREA | RISK COMMUNICATION
GOAL | State Parties use multilevel and multifaceted risk communication capacity. Real-time exchange of information, advice and opinions between experts and officials or people who face a threat or hazard (health or economic or social wellbeing) to their survival, so that informed decisions can be made to mitigate the effects of the threat or hazard and protective and preventive action can be taken. This includes a mix of communication and engagement strategies, such as media and social media communications, mass awareness campaigns, health promotion, social mobilization, stakeholder engagement and community engagement.
JEE recommendations | • Document and endorse a national risk communication strategy. • Document and test existing SOPs to support and build upon the current risk communication structure. • Standardize formal assessments to evaluate and apply lessons learnt from risk communication and community engagement activities. • Train community engagement and social mobilization teams to expand community participation and planning in the risk communication process at the local level. • Develop a formal system for dynamic listening and rumour management.
JEE Indicator | R.5.1 | Risk Communication Systems (plans, mechanisms, etc.)
JEE Scores | 4
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators | Periodicity | Implementation
[8 empty] | (Monotoring and Evaluation) |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 16.1.1.1 | developent national risk communication strategy. | Working Group Meeting | Disaster committee/MOH Public relationand heath promotion | other relevent sectors | yes | National and sub national | rissk communication stategy | 1 | bar: 2020 Q4
| 16.1.1.2 | Develop SOPs for risk communication | Working Group Meeting | Disaster committee/MOH Public relationand heath promotion | other relevent sectors | No | National and sub national | SOPs for risk communication | 1 | bar: 2021 Q1
JEE Indicator | R.5.2 | Internal and Partner Communication and Coordination
JEE Scores | 4
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators | Periodicity | 2019 Q1: Implementation
[8 empty] | (Monotoring and Evaluation) |  | 2019 Q1: 2019; 2020 Q1: 2020; 2021 Q1: 2021; 2022 Q1: 2022; 2023 Q1: 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 16.2.1.1 | Test existing SOPs for risk communication | SimEX, TTX | Disaster committee/MOH Public relationand heath promotion | other relevent sectors | No | National and sub national | testing is conducted and SOPs | 2 | bar: 2021 Q2; 2023 Q2
JEE Indicator | R.5.3 | Public Communication
JEE Scores | 4
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators | Periodicity | 2019 Q1: Implementation
[8 empty] | (Monotoring and Evaluation) |  | 2019 Q1: 2019; 2020 Q1: 2020; 2021 Q1: 2021; 2022 Q1: 2022; 2023 Q1: 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 16.3.1.1 | public risk communication ,adocacy materials and rumer management system | Infrastructure/Supplies Investment, SMALL | Disaster committee/MOH Public relationand heath promotion | community representitives/relegious people other relevent parties | yes | national and subnational | development of system | 1 | bar: 2020 Q4
JEE Indicator | R.5.4 | Communication Engagement with Affected Communities
JEE Scores | 4
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators | Periodicity | 2019 Q1: Implementation
[8 empty] | (Monotoring and Evaluation) |  | 2019 Q1: 2019; 2020 Q1: 2020; 2021 Q1: 2021; 2022 Q1: 2022; 2023 Q1: 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 16.4.1.1 | simulation exercice to include community representitive | SimEX, Functional | Disaster committee/MOH Public relationand heath promotion | community representitives/relegious people /other relevent parties | Yes | national and subnational | simulation exercise conduction | 2 | bar: 2021 Q2; 2023 Q2
JEE Indicator | R.5.5 | Dynamic Listening and Rumour Management
JEE Scores | 3
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators | Periodicity | 2019 Q1: Implementation
[8 empty] | (Monotoring and Evaluation) |  | 2019 Q1: 2019; 2020 Q1: 2020; 2021 Q1: 2021; 2022 Q1: 2022; 2023 Q1: 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 16.5.1.1 | incorprated monitoring and evaluation of dynamic listening /rumer management to rumer management system | Workshop/Training, MEDIUM | Disaster committee/MOH Public relationand heath promotion | WHO ,community representitives/relegious people /other relevent parties | yes | national and subnational | monitoring and evaluation of dynamic listening /rumer management included in the system | 1 | bar: 2021 Q1

## Points of Entry
Bahrain NAPHS 2019-2023
OTHER IHR-RELATED HAZARDS AND POINTS OF ENTRY
TECHNICAL AREA | POINTS OF ENTRY
GOAL | States Parties should designate and maintain the core capacities at the international airports and ports (and where justified for public health reasons, a State Party may designate ground crossings) which implement specific public health measures required to manage a variety of public health risks.
JEE Recommendations | • Develop a multihazard public health contingency plan for each PoE with the involvement of all stakeholders. • Improve the animal quarantine capacity at PoE. • Enhance the use of IHR recommended model of ship sanitation certificates at Khalifa bin Salman port. Ensure rapid access to equipment and trained personnel for the early detection and management of ill passengers.
JEE Indicator | PoE.1 | Routine capacities are established at PoE.
JEE Scores | 3
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implemetation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 17.1.1.1 | to develop POE Vector Area of Surveillanc programme for vector surveillance and control | Infrastructure/Supplies Investment, LARGE | MOH Focal Point/NFP CAA/BAC/PMA/APMT | CAA/BAC/PMA/APMT | yes | National and subnational | comerhensive surveillance program in place | 1 | bar: 2023 Q3
| 17.1.1.2 | Improve quarantine services at POE | Infrastructure/Supplies Investment, SMALL | Bahrain Airport Company | MOH and All relevant sectors | Yes | National and subnational | quarantine services at POE improvement | 1 | bar: 2020 Q2
| 17.1.1.3 | to improve Vessel inspection at seaports for ship sanitation | Working Group Meeting | MOH | PMA/APMT | yes | National and subnational | Identification | 1 | bar: 2019 Q4
JEE Indicator | PoE.2 | Effective Public Health Response at Points of Entry
JEE Scores | 2
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 17.2.1.1 | to test a multihazard public health contingency plan for each PoE with the involvement of all stakeholders. | SimEX, Drill | point of entery authority /PMA/APMT/BAC/CAA | MOI/BDF/MTT/MOH/SCE/CG/CD | yes | National and subnational | Plan is tested and updated | 2 | bar: 2020 Q1; 2022 Q1
| 17.2.1.2 | establishment of medical services at King Fahed Causway | Infrastructure/Supplies Investment, LARGE | King Fahad Causway authority | MOH/NAHRA | No | National and subnational | Health facility established | 1 | bar: 2020 Q4

## Chemical Events
Bahrain NAPHS 2019-2023
OTHER IHR-RELATED HAZARDS AND POINTS OF ENTRY
TECHNICAL AREA | CHEMICAL EVENTS
GOAL | State Parties to have surveillance and response capacity for chemical risks or events, with effective communication and collaboration among the sectors responsible for chemical safety, industries, transportation and safe disposal.
JEE recommendations | • Update the National Chemical Profile. • Accredit an environmental sampling and analysis laboratory. • Prepare a plan for integration of a national poison facility into the MOH to include access to international toxicology databases (e.g. Poisindex) and 24/7 access to advice relating to clinical management. • Disaster Management Committee to complete and publish a chemical plan and perform multisectoral exercises. • MOH and NHRA to ensure that medical training for management of chemical cases and events is part of medical registration and develop/source training for first responders to chemical events.
JEE Indicator | CE.1 | Mechanisms are established and functioning for detecting and responding to chemical events or emergencies
JEE Scores | 4
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implemetation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 18.1.1.1 | Update the National Chemical Profile. | Working Group Meeting | Supreme Council for Environment | University of Bahrain and other relevnt secters /international experts | yes | national and subnational | updated national profile | 1 | bar: 2020 Q4
| 18.1.1.2 | Update the National Chemical Profile (Organize national inception workshop to train key stakeholders and agree on their roles; agree on project work plan; develop a monitoring and evaluation plan; and form an awareness raising strategy to be implemented throughout the project ) | Workshop/Training, MEDIUM | Supreme Council for Environment | University of Bahrain and other relevnt secters /international experts | YES | national and subnational | WORKSHOP CONDUCTED | 1
| 18.1.1.3 | To develop a plan for integration of a national poison facility into the MOH to include access to international toxicology databases and 24/7 access to advice relating to clinical management. | Working Group Meeting | Dsaster commitee | MOH | yes | national and subnational | national plan available | 1 | bar: 2020 Q1
| 18.1.1.4 | Collebratve system with Accredit lab for environmental sampling and laboratory analysis. | Routine Activity (NO COST) | Supreme Council for Environment | third party laboratory | No | national and subnational | Fanctional system | 1 | bar: 2020 Q1
| CE.2 | Enabling environment is in place for management of chemical events
JEE Indicator | 3
JEE Scores
Objective | # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 18.2.1.1 | to ensure that medical training for management of chemical cases and events is part of medical registration and develop/source training for first responders to chemical events. | Develop Curriculum/Training Programme, SMALL | MOH | NHRA/Medical schools | yes | national | traing program is developed | 1 | bar: 2023 Q3

## Radiation emergencies
Bahrain NAPHS 2019-2023
OTHER IHR-RELATED HAZARDS AND POINTS OF ENTRY
TECHNICAL AREA | RADIATION EMERGENCIES
GOAL | State parties should have surveillance and response capacity for radio-nuclear hazards/events/emergencies. It requires effective communication and collaboration among the sectors responsible for radio-nuclear management.
JEE recommendations | • Implement the recommendations from the IAEA project reports from April and November 2015. • Undertake a capability needs assessment and gap analysis across all sectors (public, private and military) on monitoring equipment and trained staff for the whole range of radiological incident scenarios. An action plan to address these gaps should consider: m creating memorandums and protocols for use of existing assets during an incident, making best use of equipment’s full capabilities; m expanding the number of assets (equipment and trained staff); and/or m requesting international assistance from the Cooperation Council for the Arab States of the Gulf or the IAEA Assistance Convention. • Continue providing training for medical and first responders to a radiological incident; include the handling of contaminated casualties and the symptoms of acute radiation syndrome. • Conduct regular training and exercise drills to test and improve the written protocols and multisector working relationships and understanding at the operational, tactical and national level.
JEE Indicator | RE.1 | Mechanisms are established and functioning for detecting and responding to radiological and nuclear emergencies
JEE Scores | 3
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 19.1.1.1 | Establish national committee from concern stakeholder to review and update the national plan, and to push for the approval of the plan in the parliament . | Working Group Meeting | National disaster committee / MOH , SCE. | MOI, MOC, Media, Bahrain red crecent society | Yes | National | updated national radiation plan | 2 | bar: 2020 Q2; 2022 Q2
| 19.1.1.2 | MOH has another TC project in strengthening occupational radiation protection systems BAH9007 where a physician will be sent for fellowship training in the handling of contaminated casualties and the symptoms of acute radiation syndrome. | Fellowship - PERSON/YEAR | MOH |  | yes | national |  | 1 | bar: 2020 Q1
JEE Indicator | RE.2 | Enabling environment is in place for management of Radiation Emergencies
JEE Scores | 3
Objective
| # | Summary of Planned Activities | Type of activity | Responsible authority(s) for Implementation including budget line holder | Collaborating Institutions | External Technical Support Required (Y/N) | Where is the action to be implemented (National or sub-national) | Output indicators (Monitoring and Evaluation) | Periodicity | 2019 Q1: Implementation
[10 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 19.2.1.1 | Establish Health Observatory system to record and map workforce in Bahrain | Infrastructure/Supplies Investment, SMALL | ,SCE,MoH/Ministry of Labour | Ministry of Education/University of Bahrain/Arabian Gulf University | No | National | System development | 2 | bar: 2019 Q4; 2022 Q2

## Sheet2
Activity | Description | Total cost estimate | USD | Column1
Working Group Meeting | Smaller number of Participants, Negligible additional costs
Meeting, SMALL | 30 Participants, Venue, Coffee Breaks & Lunch, PerDiem - PER DAY |  | 1590
Meeting, MEDIUM | 50 Participants, Venue, Coffee Breaks & Lunch, PerDiem - PER DAY |  | 2645
Meeting, LARGE | 70 Participants, Venue, Coffee Breaks & Lunch, PerDiem, International Travel - PER DAY |  | 3700
Workshop/Training, SMALL | 15 Participants, Venue, Coffee Breaks & Lunch, PerDiem - PER DAY |  | 790
Workshop/Training, MEDIUM | 30 Participants, Venue, Coffee Breaks & Lunch, PerDiem - PER DAY |  | 1590
Workshop/Training, LARGE | 45 Participants, Venue, Coffee Breaks & Lunch, PerDiem, International Travel - PER DAY |  | 2380
Printing, SMALL | Documents and Technical Material |  | 390
Printing, MEDIUM | Documents and Technical Material |  | 790
Printing, LARGE | Documents and Technical Material |  | 1320
Media, SMALL | Social Media, Video, Website, Radio, News |  | 1322 | Video creation only
Media, MEDIUM | Social Media, Video, Website, Radio, News |  | 1322 | Video creation only
Media, LARGE | Social Media, Video, Website, Radio, News |  | 1322 | Video creation only
Consultancy - NATIONAL | Salary, PER MONTH |  | 5290
Consultancy - INTERNATIONAL | Salary, PER MONTH |  | 5290
Infrastructure/Supplies Investment, SMALL | Ex: Construction, IT & Electronics, Vehicles, etc. |  | 52900
Infrastructure/Supplies Investment, MEDIUM | Ex: Construction, IT & Electronics, Vehicles, etc. |  | 13200
Infrastructure/Supplies Investment, LARGE | Ex: Construction, IT & Electronics, Vehicles, etc. |  | 300000
Develop Curriculum/Training Programme, SMALL | Considers Consultancy, Meetings, Printing, MOOC, Travel |  | 265 | per day
Develop Curriculum/Training Programme, LARGE | Considers Consultancy, Meetings, Printing, MOOC, Travel |  | 265 | per day
Investigative Activity, SMALL | Ex: M&E, Research, Project activity - Considers HR, travel, material, etc. |  | 265 | per day
Investigative Activity - MEDIUM | Ex: M&E, Research, Project activity - Considers HR, travel, material, etc. |  | 265 | per day
Investigative Activity - LARGE | Ex: M&E, Research, Project activity - Considers HR, travel, material, etc. |  | 265 | per day
Study Tour - PERSON/WEEK | Participation fees, travel, per diem |  | 265 | per day
Fellowship - PERSON/YEAR | Participation fees, travel, per diem |  | 265 | per day
Postgraduate Study - PERSON/YEAR | Participation fees, travel, per diem |  | 265 | per day
SimEX, TTX | Considers Planning Inputs, HR, and Venue |  | 0
SimEX, Drill | Considers Planning Inputs, HR, and Venue |  | 0
SimEX, Functional | Considers Planning Inputs, HR, and Venue |  | 0
SimEX, Full-Scale | Considers Planning Inputs, HR, and Venue |  | 0
Routine Activity (NO COST) | NO COST ACTIVITY